## GUIDELINES
Coalition Store 6 - Guidelines
1 | IF STORE DOES NOT CALL IN FOR THE INSTALL AT THEIR SCHEDULED TIME, CHECK THE POS INSTALL TICKET FOR INSTALLER/SITE CONTACT INFO AND CONTACT THAT PERSON TO FOLLOW UP. IF NO INFO WAS PROVIDED, NOTIFY INSTALLGROUP@KWI.COM FOR FOLLOW UP
2 | UPDATE POS INSTALL TICKET WITH ONSITE CONTACT'S NAME AND PHONE NUMBER, AS WELL AS SITE CONTACT INFO (IF NOT PREVIOUSLY NOTED)
3 | ONCE STORE CALLS IN FOR THE INSTALL, CONFIRM ALL EQUIPMENT THAT WAS ORDERED IS ONSITE AND PHYSICALLY SET UP – CHECK INSTALL TICKET FOR EQUIPMENT BEING INSTALLED. IF TECH IS CALLING IN TO SIMPLY "CHECK IN" UPON ARRIVAL, ADVISE THEM TO SETUP ALL POS EQUIPMENT AND CALL BACK WHEN COMPLETED
4 | CHECK INSTALL TICKET FOR PUBLIC IP INFO FOR REGISTERS. IF NO INFO IS NOTRED, REQUEST THIS INFO FROM THE INSTALLER/ONSITE CONTACT, AND CONFIRM CONNECTIVITY TO ALL POS IN THE STORE
5 | CONFIRM STORE'S MAIN PHONE NUMBER (FOR PRINTING ON RECEIPT) IF NOT ALREADY ON THE EOF, FIND OUT IF THEY ARE USING A PRINTER TO PRINT REPORTS; AND CONFIRM WHETHER IT'S LOCAL (USB CONNECTION TO POS) OR NETWORKED
6 | COMPLETE INSTALL/GO LIVE CHECKLIST
7 | WHEN TESTING REGISTERS CONFIRM: STORE NUMBER, ADDRESS AND PHONE NUMBER PRINTING ON RECEIPT, DATE & TIME, TIMEZONE
8 | UPDATE INSTALL TICKET AND EMAIL VKHAN@KWI.COM INSTALLGROUP@KWI.COM AND DRIVEINSTALLGROUP@KWI.COM WITH ALL NECESSARY INFO (INCLUDING HARDWARE/IP'S/ISSUES/ETC.) - SEE FORMAT BELOW:
Volcom #141115 Installed 1 TP7K Register Installed/ 1 Customer Display / Epson TM88V Printer/ Preh Keyboard/DS9208 Scanner/I6780 Pinpad/HP Officejet report printer Debit/Credit Auth Windows Key: Windows 7 Ultimate Reg1: 7KBMP-FJ2J3-4JV8R-8J93B-Q7CTJ Planned 1st Day of Receiving (EOD): 3/4/14 Planned 1st Day of Live Sales (EOD): 3/4/14 Phone#808-922-1026 EOF & Install Sheets Located: T:\POS CONFIG TEAM\Installation Documents and Electronic Tracking-12-23-10\Coalition 6\Installation by Client-Store\Volcom\141115 Please add store to polling Issues: - Amex not processing - Emailed merchant services - Pinpads not onside - needs pinpads claimed and debit tested
9 | FILL OUT PROJECT VITALS TAB WITH ALL NECESSARY INFO

## PROJECT VITALS
Coalition Store 6 - Project Vitals
|  |  | YESORNO | STORE TYPE | INSTALL TYPE | INSTALLER | BOARD TYPE | COALITION VERSION | OS | STORE CONNECTIVITY | MERCHANT SVC | CREDIT | PINPADS | GIFT | POS PRINTER | POS SCANNER | MONARCH | NETWORK PRINTER
COMPLETED ON: |  |  | YES | RETAIL | RE-OPENING/MOVE | SELF | TP2K-A | COAL5 | WIN2K | PCA | KWIMS | AJB CREDIT ONLY | NO | YES- PROFIT POINT | DT50 | FUJITSU SLIMSCAN 1200 SERIAL | MONARCH 9416XL | OKIDATA B411DN (B/W, NETWORKED)
COMPLETED BY: |  |  | NO | OUTLET | NEW STORE | FUJITSU | TP2K-M | COAL6 | WINXP | VNC 1/FACTOR | OTHER | AJB CREDIT AND DEBIT | I6580 SERIAL | YES - BRIGHTON (FIRST DATA/VALULINK) | DT50-I | SYMBOL M2004 CYCLONE PS2-WEDGE | MONARCH 9855 | OKIDATA B411D (B/W, LOCAL)
|  |  |  | OTHER (SEE NOTE) | UPGRADE/CONVERSION | KWI | TP3K-M |  | WIN7 | VNC 2/FACTOR | NON-INTEGRATED | NON-INTEGRATED | I6580 USB | YES - EQUINOX | DT50-II | SYMBOL DS9808 PS2-WEDGE |  | OKIDATA C330DN (COLOR, ETHERNET)
DETAILS: | PARAMETERS | NOTES |  |  | DRIVE REPLACEMENT |  | TP3K-XL2 |  | POSREADY7 | PCA 12.5 (BEN SHERMAN) |  | SEMI-INTEGRATED (QVC/VF) | I6780 SERIAL | NO | DT50-III | SYMBOL DS9808 USB |  | CLIENT-SUPPLIED (SEE NOTE)
CLIENT NAME: | [6 empty] | TP7K - AIO | [5 empty] | I6780 USB |  | DT50-IV | SYMBOL LS9208 PS2-WEDGE
STORE #: | [6 empty] | TP7K - F-SERIES | [5 empty] | I3070 SERIAL |  | TM88-III | SYMBOL LS9208 USB
STORE PHONE #: | [12 empty] | I3070 USB |  | TM88-IV | SYMBOL DS6708 PS2-WEDGE
STORE TYPE: | [12 empty] | VERIFONE |  | TM88V | SYMBOL DS6708 USB
# OF REGISTERS: | [15 empty] | SYMBOL 470 PS2-WEDGE
IP LINE AT PLT: | [15 empty] | SYMBOL MT2070 PS2-WEDGE
KWI INSTALL TICKET #: | [15 empty] | SYMBOL MT2070 USB
INSTALL TYPE: | [15 empty] | SYMBOL DS9208 USB
INSTALLER:
SET UP IN BACK OFFICE:
TAX TABLE SET UP:
IS MASTER AVAILABLE:
SALES TAX RATE:
EXTERNAL/PUBLIC IP - REG1:
EXTERNAL/PUBLIC IP - REG2:
IP ADDRESS REG1:
IP ADDRESS REG2:
SUBNET:
GATEWAY:
DNS1:
DNS2:
NETWORK PRINTER IP:
REG 1 WINDOWS KEY:
REG 2 WINDOWS KEY:
VARIABLES:
BOARD-TYPE
COALITION VERSION:
OS:
STORE CONNECTIVITY
MERCHANT PROCESSING:
CREDIT:
PINPADS:
GIFT:
TELECHECK CHECKS:
CUSTOMER DISPLAY:
PRINTER MODEL:
POS SCANNER MODEL:
SYMBOL 3000:
MONARCH PRINTER MODEL:
NETWORK PRINTER MODEL:
MPOS:
ATTACHMENTS:
EOF
TEST RECEIPTS
VAR SHEET (IF APPLICABLE)

## CONT CONFIG
Coalition Store 6 - Controller Configuration
v2.0
Step: | Description | Notes: | Completed by: | Date/Time:
COPY AND PASTE THE INSTALL CHECKLIST TO THE INSTALL FOLDER YOU ARE CONFIGURING FOR
Path for checklist: T:\POS CONFIG TEAM\Install Docs and Electronic Tracking-12-23-10\Coalition 6\Prod Docs & Required Files\Auto Configuration and Install Docs
Right click Install Checklist, Left Click Copy
Navigate to your Install folder and paste the Install checklist
Rename the checklist using the following format:
XXXXXX.ONE-CLICK.COAL 6x .POS CONFIG-GO LIVE CHECKLIST. V1.0 (X= 6 DIGIT STORE #)
1 | ***CONFIRM CORRECT BUILD & PLATFORM IS ON DRIVE***
***BEFORE BEGINNING CONFIG***
1.1 | Check the Install ticket for whats listed that the store is suppose to have and if not sure
1.2 | confirm with purchasing dept and compare with whats on drive
1.3 | CONFIRM THE CORRECT OS PLATFORM(XP, WIN7) BY GOING TO PROPERTIES OF MY COMPUTER
1.4 | Confirm correct build (Register Type/Model) by going to C:\ ….
1.5 | IF XL2 Drivers folder = XL2 build, IF 7000AIO Drivers folder = TP7 AIO BUILD
1.6 | To differ between a TP7K Full & TP7K AIO Image Build is to look in regedit: HKEY_Local_Machine>Software>OLEforRetail>Line Display
1.7 | If you do not see a VF35 folder then it’s a TP7K Full Image, if the VF35 folder is there then its TP7K AIO image
1.8 | KEY IN HERE WHAT TYPE OF PLATFORM & BUILD IS THIS:
2 | SETUP RAID UTILITY
2.1 | TP3K With LOCAL PAM ICON ON DESKTOP:
2.2 | TP3K: with register powered off insert both drives, power up register and hold down Ctrl+F to enter the raid utility
2.2 | Select Option 4 to delete the array, it prompt to Delete, hit delete key
2.2 | Select "N" to create only, *****DO NOT SELECT DELETE BOOT SECTOR******
2.2 | select Option 2 to change from JBOD TO SPARE
2.2 | Select Option 1 and hit the space bar to change the auto setup to SECURITY, hit ctrl+Y to save changes
2.2 | and select N TO CREATE ONLY
2.2 | FOR DETAILED DIRECTIONS ON SETTING UP RAID FOR TP3K:
2.2 | T:\POS CONFIG TEAM\Raid Procedure for TP3K
2.2 | RAID installation v1.04.doc (??=current version level) - user kwipos password 9retail9
3 | XL2:
3.1 | with register powered off insert both drives, power up register and hold down Ctrl+I to enter the Raid Utility
3.2 | In Raid Utility select Option #2 Delete Raid, IT WILL PROMPT TO HIT "DELETE" KEY to confirm
3.3 | Hit delete key and then ESC Key to Exit
3.4 | Power off register and remove Raid Drive, boot up register
3.5 | Once register is booted up go into the XL2 raid setup screen:
3.6 | Cick on Start>Programs>Intel Matrix Storage Mgr>Intel Matrix Storage Console
3.7 | At top of screen select view, select basic mode
3.8 | Insert the raid drive in Channel 2
3.9 | from the raid utility screen on the right side under DETAIL do the following:
4 | Select the top option "Protect Data from HD Failure with RAID 1
4.1 | Click YES to create RAID1 Volume to begin RAID PROCESS
5 | Activate/Register Win7 License Key
5.1 | Navigate to Control
5.2 | Open System
5.3 | Select Change Product Key
5.4 | Type new Win7 License key (must be exact)
5.5 | Select OK
5.6 | Key will Activate and Register
6 | Label Hard Drives
7.1 | Use correct Hard-drive Label
7.2 | add store number
7.3 | check appropriate drive type
7.4 | check appropriate channel
7.5 | add image date
7.6 | add config date
8 | Notate Information Needed to build a drive
8.1 | Store name
8.2 | Full Address
8.3 | Phone Number (do not use brackets or dashes ex:5555555555
8.4 | What type of store is this? Ex:retail, outlet, concept, etc
8.5 | If you are not sure if the store is RETAIL OR OUTLET then do the following: check MySQL to confirm the TYPE of store
8.6 | Go into the KWIki Knowledge base, on the lefthand side under HELPDESK QUICK LINKS select SQL Search Queries
8.7 | In the Table of Contents for SQL Search Queries select STORE NAME/NUMBER RELATED SEARCHES
8.8 | copy the entire contents of the query search CLIENT TYPE(OUTLET OR RETAIL)
8.9 | Go into MYSql and connect to the server the store you are installing for is on
8.1 | Paste the contents you copied into the command line for MYSql, key in the 6 digit store number in place of 'STORE NUMBER'
Leave the quotes, click the execute button
8.11 | It will list the store number, client number and address, the client number will show 100=RETAIL OR 101=OUTLET
8.12 | IF YOU ARE NOT SURE OF THE ABOVE ASK A SENIOR FOR HELP
Client Configuration
9 | Load Client Master
9.1 | NOTE HERE Master files type/date stamp - ex. What Type(outlet/retail) Latest date of zip files
9.2 | Copy client specific master zip files to c:\nsb\coalition\download\config\master (the following zip files are used but are not required by all clients - edu.zip, graphics.zip,dotnet.zip,ini,zip)
9.3 | File Transfer the RegisterInstall.zip located: T:\POS CONFIG TEAM\Installation Documents and Electronic Tracking-12-23-10\Coalition 6\Production Documents and Required Files\Auto Configuration and Install Docs\Auto Config
9.4 | FILE TRANSFER TO C:\
9.5 | UNZIP TO C:\ ***** USING FOLDER NAMES *****
9.6 | Open RegisterInstall folder
9.7 | Run "RegisterInstall.bat
9.8 | Fill in prompted information
9.9 | When prompted to re-start select "yes"
9.1 | Verify all Processed in EDU Directory (if any file(s) errored out, have .ERR go to step 9.11, otherwise proceed to step 10.0)
9.11 | Stop NSB Services
9.12 | Start NSB Services
9.13 | Rename the .ERR file(s) to .DCN to Re-Process file(s)
10 | Once Register completes reboot go into store functions and close register:
10.1 | Select F1 Unlock POS, Select F6 Store functions and signon
10.2 | Select F7 Initial Tray IN, Log IN
10.3 | Tray number 1 should Populate, Select F1 OK, Select F1 for close draw prompt
10.4 | Select F5 Close Register, Select F1 Continue, Select F2 NO for not to print register totals report
10.5 | Select F1 OK to Continue with Final Pickup Declaration
10.6 | Select F8 Continue, Select F1 OK to accept pickup, Select F1 OK to accept Media Summary
If you are configuring for 3 or more registers for a new location (Addt'l Steps)
On the Controller
10.12 | If applicable, obtain the store's current Till Float amount
10.13 | Navigate to c:\nsb\coaltion\edu
10.14 | edit 07_KWI_workstation.processed a) Add new workstation in [Data.4] section b) save and reprocess (wait for process to complete)
10.15 | edit 22_KWI_TILL.processed a) Add new Till in [Data.4] section(follow format for existing Tills - be sure to add both lines, see Till 3 example below: Till,3,,TILL,3,Till 3,WKST,,3,200.00, Tender,1,200.00,200.00 b) For all Registers/Tills, adjust if necessary the store's current Till Float, see the following highlighted example of $200.00 Float fields for Till 3: Till,3,,TILL,3,Till 3,WKST,,3,200.00, Tender,1,200.00,200.00 c) THE AMOUNT OF REGISTERS IN THE [Data.4] OF 22_KWI_TILL.Processed SHOULD MATCH EXACTLY WITH AMOUNT OF REGISTERS LISTED IN THE [Data.4] SECTION OF 007_KWI_WORKSTATION.Processed d) save and reprocess (wait for process to complete)
10.16 | After making changes to the TILL & WORKSTATION FILES, CONFIRM the files did not error out after reprocessing them
10.17 | Confirm Workstation Fields are setup correclty:
10.18 | Check Workstation_NO, Workstation_name, Workstation Desc, WRKST_Comp_Name - SCROLL THROUGH ALL FIELDS
10.19 | Open SQL Server Management Studio Express from the desktop
10.2 | Go to USICOAL Database, Open Tables and Right Click WORKSTATION, Left Click Open, for POSReady you would click Edit
10.21 | You need to CONFIRM the THIRD RECORD and on as this SHOULD NOT BE DEFAULTED as REGISTER 2 ON ALL PRIMARY REGISTERS
Store/Register Configuration
11 | AJB(FIPAY)
CONFIRM CORRECT AJB BUILD IS INSTALLED
11.0.1 | New stores: AJB 20394
11.0.2 | Drive Replacements at 1-Reg stores: AJB 20394
11.0.3 | Drive Replacements at Multi-Reg store: Match “good” register and install for that AJB Build
11.0.4 | EQUINOX: PELASE USE 'AJB20394 EQUINOX ONLY' IN THE POSTINSTALL 6X FOLDER (README IN FOLDER)
11.0.5 | Exceptions would be for: 7FAM, Bribor, Brighton, Equinox, Lucy, QVC
FIPAY FILES
11.1 | Create the fipay file by going to the intranet and log into the PCI Webtool
11.2 | select build AJB Files, select client, select store number you are building for
11.3 | select file type(if not sure about this ask a senior for help)
11.4 | select get registers, this will display all register numbers in register box
11.5 | select number corresponding to registers you are building for & click the submit button to build files
11.6 | You will then see a message listing what server and path the file has been built
11.7 | Locate the fipay file(s) on the server and pull them back to: the Store's Install folder you are configuring for
11.8 | ON THE POS:
11.9 | Navigate to c:\wansupp
11.1 | add store/register specific fipay file
11.11 | Store/register specific fipay file gets renamed to fipaypincs_config.xml
11.12 | add store/register specific vxn_param.dat if applicable
11.13 | Confirm that ALL xml's in ALL registers have the SAME Merchant #
11.14 | Open XML in IE; search for "xxxxxx" (where "xxxxxx"= store #) - Confirm seen in "//dafault_store = "######"
11.15 | Open XML in IE; search for "999999" - Confirm this is NOT seen in "//dafault_store = "######"
11.16 | Refresh the fipay service in services.msc
11.17 | THE ABOVE NEEDS TO BE DONE (REPEATED) FOR ALL REGISTERS
**** YOU MUST REMOVE THE FIPAY FILE FROM THE STORE'S INSTALL FOLDER****
If this is a Windows 7 store, skip to Step 12.3
If this is a Windows XP store, continue to Step 12.1
If this is a POSReady store, continue to Step 12.2
12 | Set Windows Tasks (Look for OS version below)
12.1 | Set Windows Tasks (XP)
Run tasks and set to correct store number and reset password on all tasks (password 9retail9)
12.2 | Set Windows Tasks (POS READY)
Run tasks from Desktop and set to correct store number and reset password on all tasks (password 9retail9)
12.3 | Set Windows Tasks (Win7)
12.3.1 | Install Win7 Scheduled Task Fix
12.3.2 | Download files located in Install Docs\ Coalition 6\Prod Docs\Post Install\Win7SchtaskFix Folder
12.3.3 | Run Update2.bat file
12.3.4 | Done
13 | Tax Rate
For Drive Replacements: Check TSARC (if possible) / Check Tax Files by State / Confirm Tax Rate with the Store
13.1 | Check for Special Tax files (T:\StoreSystemsDevelopment\Level 4\Tax\TAX FILES FOR STATES)
13.2 | Navigate to c:\nsb\coalition\edu
13.3 | edit 12_KWI_Tax.processed
13.4 | Update store number and tax rate
13.5 | reprocess file
14 | Process Bulk Files
14.1 | Use tab below - BULK File Process
14.2 | AFTER ALL FILES HAVE FINISHED PROCESSING, REPROCESS THE FOLLOWING FILES IN ORDER ONLY IF THERE
ARE CLIENT SPECIFIC NON_MERCH FILES:
14.3 | 1. KWI_NONMERCH, 2. CLIENT SPECIFIC NON_MERCH FILES, 3. ZIPTAX
15 | Confirm MW Dbase Space Available
15.1 | AFTER MW CUST & PURCH HISTORY FILES ARE COMPLETED PROCESSING DO THE FOLLOWING:
15.2 | check the size of the space available for MW:
15.3 | at the desktop open the SQL Server Management Studio Express & log in
15.4 | Right Click MW, Left Click Properties
15.5 | CONFIRM SPACE AVAILABLE IS CORRECT IF ITS BETWEEN 1M-100M FOLLOW INCREASE DISK SPACE
15.6 | AVERAGE SPACE AVAILABLE IS 399. MB
16 | *******INCREASE DISK SPACE FOR MW*******
16.1 | To increase disk space for MW, follow documentation located:
16.2 | T:\POS CONFIG TEAM\Installs Troubelshooting\6X\MW\MW Increase Size
16.3 | MW_Data - change size to 1024
16.4 | MW_LOG - change size to 512
16.5 | CONFIRM CUST NUMBER IS CORRECT
16.6 | Open SQL Server Management Studio Express from desktop
16.7 | Select Databases, Select MW, Select Tables, scroll down and right click on Parameter_system
16.8 | Select Open table, at right, scroll over and look for next_cust_no, click in field to edit and key in correct cust number if necessary(example store 7 would be 7000001) no leading zero's (example store 141 would be 141000001)
17 | UPDATE NAV(VIA INTERNET CONNECTION)
17.1 | Double click on the NAV Shield at bottom right in system tray
17.2 | click on update, NAV Definitions should download and update
SETUP LOGPAS FOR CHARGESEND
18 | backup logpas in c:\nsb\coalition\file and transfer the logpas located in :
18.1 | T:\POS CONFIG TEAM\Installation Documents and Electronic Tracking-12-23-10\Coalition 6\Production Documents and Required Files\Post Install\All OS-Global\Logpas
18.2 | FOLLOW THE README INSTRUCTIONS FOR EDITING LOGPAS, 5 FIELDS CONTAINING BACKOFFICE NEED TO BE EDITED
18.3 | SAVE CHANGES AND EXIT
19 | Post Install
19.1 | See Post Install Tab
19.2 | Notate Coalition version from main screen (Example: 6.2.6.164.42)

## PRIMARY CONFIG
Coalition Store 6 - Primary Configuration
v2.0
Step: | Description | Notes: | REG2: | DATE/TIME | REG3: | DATE/TIME
COPY AND PASTE THE INSTALL CHECKLIST TO THE INSTALL FOLDER YOU ARE CONFIGURING FOR
Path for checklist: T:\POS CONFIG TEAM\Install Docs and Electronic Tracking-12-23-10\Coalition 6\Prod Docs & Required Files\Auto Configuration and Install Docs
Right click Install Checklist, Left Click Copy
Navigate to your Install folder and paste the Install checklist
Rename the checklist using the following format:
XXXXXX.ONE-CLICK.COAL 6x .POS CONFIG-GO LIVE CHECKLIST. V1.0 (X= 6 DIGIT STORE #)
1 | ***CONFIRM CORRECT BUILD & PLATFORM IS ON DRIVE***
***BEFORE BEGINNING CONFIG***
1.1 | Check the Install ticket for whats listed that the store is suppose to have and if not sure
1.2 | confirm with purchasing dept and compare with whats on drive
1.3 | CONFIRM THE CORRECT PLATFORM(XP, WIN7) BY GOING TO PROPERTIES OF MY COMPUTER
1.4 | Confirm correct build by going to C:\, IF XL2 Drivers folder = XL2 build
1.5 | IF 7000AIO Drivers folder = TP7 AIO BUILD
1.6 | To differ between a TP7K Full & TP7K AIO Image Build is to look in regedit: HKEY_Local_Machine>Software>OLEforRetail>Line Display
1.7 | If you do not see a VF35 folder then it’s a TP7K Full Image, if the VF35 folder is there then its TP7K AIO image
1.8 | KEY IN HERE WHAT TYPE OF PLATFORM & BUILD IS THIS:
2 | Activate/Register Win7 License Key
2.1 | Navigate to Control
2.2 | Open System
2.3 | Select Change Product Key
2.4 | Type new Win7 License key (must be exact)
2.5 | Select OK
2.6 | Key will Activate and Register
3 | Label Hard Drives
3.1 | Use correct Hard-drive Label
3.2 | add store number
3.3 | check appropriate drive type
3.4 | check appropriate channel
3.5 | add image date
3.6 | add config date
4 | Notate Information Needed to build a drive
4.1 | Installers Name
4.2 | 6 Digit Store Number
4.3 | Register # you are configuring (Ex. Reg2, Reg3, etc.)
4.4 | What type of store is this? Ex:retail, outlet, concept, etc
4.5 | Transfer (if applicable) DOTNET.zip, GRAPHICS.zip, INI.ZIP to c:\nsb\coalition\download\config\master
4.6 | NOTE Master files type/date stamp - eg. What Type (Outlet/Retail) / Latest date of zip files
5 | Configuring the Register
5.1 | File transfer the RegisterInstall folder located: T:\POS CONFIG TEAM\Installation Documents and Electronic Tracking-12-23-10\Coalition 6\Production Documents and Required Files\Auto Configuration and Install Docs\Auto Config
5.2 | FILE TRANSFERR TO C:\
5.3 | UNZIP to C:\ ***** USING FOLDER NAMES *****
5.4 | Open RegisterInstall Folder
5.5 | Run RegisterInstall.bat
5.6 | Fill in prompted Information
5.7 | Select "Yes" to restart
5.8 | Select "Yes" to restart controller
5.9 | Select "Yes" to restart primary
6 | File Updates
6.1 | On the CONTROLLER open Replication Manger
6.2 | Update computer name
6.3 | look for register just added (will not show until POSstart on register #2 is complete)
6.4 | update level should be lower or equal to the level of the controller
6.5 | note:coaltion may fail load on primary registers, once repliction levels are updated-relaunch coalition
6.6 | force a BCN update for both usicoal and posconfig
7 | AJB(FIPAY)
7.0.1 | CONFIRM CORRECT AJB BUILD IS INSTALLED
7.0.2 | New stores: AJB 20394
7.0.3 | Drive Replacements at 1-Reg stores: AJB 20394
7.0.4 | Drive Replacements at Multi-Reg store: Match “good” register and install for that AJB Build
7.0.5 | EQUINOX: PLEASE USE 'AJB20394-EQUINOX ONLY' IN THE POSTINSTALL 6X FOLDER (README IN FOLDER)
7.0.6 | Exceptions would be for: 7FAM, Bribor, Brighton, Equinox, Lucy, QVC
FIPAY FILES
7.1 | Navigate to c:\wansupp
7.2 | add store/register specific fipaypincs_config.xml
7.3 | Confirm that ALL xml's in ALL registers have the SAME Merchant #
7.4 | Open XML in IE; search for "xxxxxx" (where "xxxxxx"= store #) - Confirm seen in "//dafault_store = "######"
7.5 | Open XML in IE; search for "999999" - Confirm this is NOT seen in "//dafault_store = "######"
7.6 | **** YOU MUST REMOVE THE FIPAY FILE FROM THE STORES INSTALL FOLDER****
If this is a Windows 7 store, skip to Step 10
If this is a Windows XP store, continue to Step 8
If this is a POSReady store, continue to Step 9
8 | Set Windows Tasks (XP)
8.1 | Run tasks and set to correct store number and reset password on all tasks (password 9retail9)
9 | Set Windows Tasks (POS READY)
9.1 | Run tasks from Desktop and set to correct store number and reset password on all tasks (password 9retail9)
10 | Set Windows Tasks (Win7)
10.1 | Start
10.2 | In the search bar type (without quotes) "taskschd.msc" and press enter
10.3 | Select "task scheduler library" on top left
10.4 | Beginning with DCN Move
10.5 | Double click each task
10.6 | Select "Change User or Group"
10.7 | Type (without quotes) "kwipos" in the white box and press enter
10.8 | Select OK
10.9 | When promted for a password type (without quotes) "9retail9"
10.1 | Selct OK
10.11 | Repeat for all remaining tasks
10.12 | Exit program when complete
If you are adding a register greater than REG2 to an existing location (Addt'l Steps)
11.0 | On the Controller
11.1 | If applicable, obtain the store's current Till Float amount & Last Trans# for each Register
11.2 | Navigate to c:\nsb\coaltion\edu
11.3 | edit 07_KWI_workstation.processed a) Add new workstation in [Data.4] section b) save and reprocess (wait for process to complete)
11.4 | edit 22_KWI_TILL.processed a) Add new Till in [Data.4] section(follow format for existing Tills - be sure to add both lines, see Till 3 example below: Till,3,,TILL,3,Till 3,WKST,,3,200.00, Tender,1,200.00,200.00 b) For all Registers/Tills, adjust if necessary the store's current Till Float, see the following highlighted example of $200.00 Float fields for Till 3: Till,3,,TILL,3,Till 3,WKST,,3,200.00, Tender,1,200.00,200.00 c) THE AMOUNT OF REGISTERS IN THE [Data.4] OF 22_KWI_TILL.Processed SHOULD MATCH EXACTLY WITH AMOUNT OF REGISTERS LISTED IN THE [Data.4] SECTION OF 007_KWI_WORKSTATION.Processed d) save and reprocess (wait for process to complete)
After making changes to the TILL & WORKSTATION FILES, CONFIRM the files did not error out after reprocessing them
11.5 | Reset Replication a) Run c:\ResetReplication.bat on the Controller Register b) Wait for ResetReplication.bat to complete c) Run c:\ResetReplication.bat on all needed Primary Registers (POS load might fail on Primary Registers until replication update is complete)
11.6 | Verification a) Wait until the POS is running on all Registers b) On Controller desktop, launch NSB.Repl.Monitor.exe c) Verify that all required registers are listed in the Current Status section
11.7 | TILL SETUP - GO TO EACH REGISTER a) Go to Store Functions look for the Orange Button "Initial Tray In" b) If No, select "Cancel/Esc" to exit and Go to step 11.8 c) If Yes, Perform the "Initial Tray In" follow prompts to complete the procedure (verify that the "Tray Log In" number that auto populates matches your Register #) d) Goto step 11.9
11.8 | Go to Manager Functions > KWI Help Desk Tools > Cash Office > Till Maintenance a) Select "Tray In/Out" b) Go to Store Functions look for the Orange Button "Initial Tray In" c) Perform the "Initial Tray In" follow prompts to complete the procedure (verify that the "Tray Log In" number that auto populates matches your Register #)
11.9 | IF YOU ARE UPDATING THE LAST TRANS#, PERFORM THE FOLLOWING STEPS FOR EACH REGISTER: a) follow steps to Update Next_transaction_no (Please utilize "Last Trans" process to determine Next_transaction_no) b) Kill POS c) Click Stop Register Services from desktop d) Open SQL Server Management Studio Express from desktop e) Go to USICOAL Database and right click on wrkst_local_data f) Select Open/edit Table - wrkst_local_data g) Enter Last Trans# in the "NEXT_TRN_NO" column h) Exit SQL Server Management Studio i) Click Start Register Services from desktop j) Click POS from desktop
12 | ON ALL PRIMARY REGISTERS GREATER THAN 2
12.1 | IF YOU ARE INSTALLING 3 OR MORE REGISTERS, THE PRIMARY REGISTERS 3 AND BEYOND NEED THE WORKSTATION DB CHANGED
AS THE WORKSTATION DB IS DEFAULTED TO 2 IN ALL FIELDS,
12.2 | Confirm Workstation Fields are setup correclty:
Check Workstation_NO, Workstation_name, Workstation Desc, WRKST_Comp_Name - SCROLL THROUGH ALL FIELDS
12.3 | Open SQL Server Management Studio Express from the desktop
12.4 | Go to USICOAL Database, Open Tables and Right Click WORKSTATION, Left Click Open, for POSReady you would click Edit
12.5 | You need to CONFIRM the THIRD RECORD and on as this SHOULD NOT BE DEFAULTED as REGISTER 2 ON ALL PRIMARY REGISTERS
FROM 3 AND BEYOND on the controller
on primary registers 3 and beyond there will only be one record, scroll through all fields and make changes, the fields will be defaulted to "2"
12.6 | REBOOT ALL REGISTERS INCLUDING THE CONTROLLER
12.7 | IF YOU ARE NOT SURE ASK A SENIOR ANALYST FOR HELP
13.0 | UPDATE NAV(VIA INTERNET CONNECTION)
13.1 | Double click on the NAV Shield at bottom right in system tray
13.2 | click on update, NAV Definitions should download and update

## BULK FILE PROCESS
Coalition Store 6 - BULK File Creation
v2.0
Store Number:
Store Phone Number:
Date of BULK File Build:
* Make sure the purch_history folder on the server has no data
Step: | Description | Completed by:
1 | Log into PCI WebTools
2 | Select Generic Downloads and click submit
3 | Files to build
3.1 | Use the pull down box to select a client then click Go
3.2 | Highlight Store number in the left box
3.3 | Highlight ITEM in the right box
3.4 | From File Type select BULK
3.5 | Leave Build Type as Non-Prod
3.6 | Click Submit
4 | After Build Completes
4.1 | Select Go (Client name will default to the last used)
4.2 | Highlight Store Number in the left box (may already be highlighted from last build)
4.3 | Highlight all in the right box EXCEPT - Item, Cust, Purch
4.4 | From File Type select Full
4.5 | Leave Build Type as Non-Prod
4.6 | Click Submit
5 | To Build Customer/Purchase File
5.1 | Before building verify KWI does not keep a file locally for the client you are creating
5.2 | Select Go (Client name will default to the last used)
5.3 | Highlight Store Number in the left box (may already be highlighted from last build)
5.4 | Highlight Cust, Purch in the right box
5.5 | From File Type select Full
5.6 | Leave Build Type as Non-Prod
5.7 | Click Submit
6 | Transfer Files Locally
6.1 | Log into the server where the Client data is stored
6.2 | Example:
6.3 | kwi8.kligerweiess.net
6.4 | directory - /usr2/pandora/Mra/AUTO
6.5 | open the bulk folder
6.6 | copy stores bulk (XXXXXX.zip - XXXXXX= store number) to a created store folder on the c: drive
6.7 | Open the NON_PROD folder
6.8 | copy remaining files to the same folder as step ??
6.9 | Navigate to the above folder
6.1 | rename the zip file adding the work BULK after the store number
6.11 | Example:
6.12 | 163091BULK.zip
6.13 | Open the zip file
6.14 | Add any extra files created for the store - remember there may not be any
6.15 | close the zip
6.16 | copy the zip file to the store build folder in POS Config Team
7 | Transfer cust file Locally
7.1 | Log into the server where the Client data is stored
7.2 | Example:
7.3 | kwi8.kligerweiess.net
7.4 | directory - /usr2/pandora/Mra/AUTO
7.5 | open the Purchase history folder
7.6 | copy the XXXXXX.zip to your saved local folder (XXXXXX=store number)
7.7 | Navigate to the above folder
7.8 | rename the zip file adding the work CUST after the store number
8 | Transfer Zip files to the store
8.1 | transfer and unzip the item zip file to c:\nsb\coalition\edu
8.2 | transfer and unzip cust zip to c:\nsb\storecrm\import
9 | Process Files
File Process Order:
9.1 | Depts.txt
9.2 | items.txt
9.3 | depts2.txt
9.4 | items2.txt
9.5 | promo.txt (if exists)
9.6 | empprom2.txt
9.7 | groupXX.txt
9.8 | store2.txt
9.9 | Employee.txt
10 | ziptax.txt
10.1 | mixmatch.txt
10.2 | procoup.txt
WARNING
Some of the above files may not exist
10 | Process MW Customer Data
10.1 | Place cust & purch files in c:\nsb\storecrm\import
10.2 | start
10.3 | run
10.4 | cmd
10.5 | cd \nsb\StoreCRM\bin
10.6 | run textio - import
10.7 | Confirm import processed:
C:\nsb\storecrm\import\logs\implog.log
scroll down in log and make sure there are no errors
make sure at bottom of file it shows"Textio.exe import terminated successfully"

## REMOVE PRIMARY REGISTER
Coalition Store 6 - REMOVE PRIMARY REGISTER
v2.0
Store Number:
Primary Register # to be removed
Step: | Description | Completed by:
1.0 | If applicable, obtain the store's current Till Float Amount & Last Trans#
2.0 | 007_KWI_WORKSTATION.Processed
2.1 | Navigate to c:\nsb\coalition\edu
2.2 | Edit 007_KWI_WORKSTATION.Processed - scroll to bottom to [Data.4] section
2.3 | For target WORKSTATION /REGISTER # to be removed, delete the entire line
2.4 | Process the file by changing the suffix to .dcn
2.5 | Wait for the dcn process to complete
3 | 022_KWI_TILL.Processed
3.1 | Navigate to c:\nsb\coalition\edu
3.2 | Edit 022_KWI_TILL.Processed - scroll to bottom to [Data.4]
3.3 | For target Register # to be removed, delete the entire Till # line and delete the entire Tender line directly below, see the following Till 2 example: Till,2,,TILL,2,Till 2,WKST,,2,200.00 Tender,1,200.00,200.00
3.4 | For the remaining Registers/Tills, adjust if necessary the store's current Till Float, see the following highlighted example of Float fields for Till 3: Till,3,,TILL,3,Till 3,WKST,,3,200.00, Tender,1,200.00,200.00
3.5 | THE AMOUNT OF REGISTERS IN THE [Data.4] OF 22_KWI_TILL.Processed SHOULD MATCH EXACTLY WITH AMOUNT OF REGISTERS LISTED IN THE [Data.4] SECTION OF 007_KWI_WORKSTATION.Processed
3.6 | Process the file by changing the suffix to .dcn
3.7 | Wait for the dcn process to complete
4.0 | ResetReplication.bat
4.1 | Run c:\ResetReplication.bat on the Controller Register
4.2 | Wait for ResetReplication.bat to complete
4.3 | Run c:\ResetReplication.bat on all needed Primary Registers
4.4 | Verify that all Registers have Rebooted after ResetReplication.bat completes
5.0 | Verification
5.1 | Wait until the POS is running on all Registers
5.2 | On Controller desktop, launch NSB.Repl.Monitor.exe
5.3 | Verify that the removed Register is not listed in the Current Status section
6.0 | TILL SETUP - GO TO EACH REGISTER
6.1 | a) Go to Store Functions look for the Orange Button "Initial Tray In" b) If No, select "Cancel/Esc" to exit and Go to step 6.2 c) If Yes, Perform the "Initial Tray In" follow prompts to complete the procedure (verify that the "Tray Log In" number that auto populates matches your Register #) d) Goto step 6.3
6.2 | Go to Manager Functions > KWI Help Desk Tools > Cash Office > Till Maintenance a) Select "Tray In/Out" b) Go to Store Functions look for the Orange Button "Initial Tray In" c) Perform the "Initial Tray In" follow prompts to complete the procedure (verify that the "Tray Log In" number that auto populates matches your Register #)
6.3 | If applicable, follow steps to Update Next_transaction_no (Please utilize "Last Trans" process to determine Next_transaction_no)
6.4 | FOR EACH REGISTER, PERFORM THE FOLLOWING STEPS: a) Kill POS b) Click Stop Register Services from desktop c) Open SQL Server Management Studio Express from desktop d) Go to USICOAL Database and right click on wrkst_local_data e) Select Open/edit Table - wrkst_local_data f) Enter Last Trans# in the "NEXT_TRN_NO" column g) Exit SQL Server Management Studio h) Click Start Register Services from desktop i) Click POS from desktop

## AERO IP SCHEME
Aerosoles - IP Scheme
v2.0
Store Number:
Step | Description | Completed by:
For stores numbered less than 197800; continue to step 1a
For stores numbered greater than 197800; skip to step 2a
1 | Set Controller IP (<800)
1.1 | ip address - 172.16.<storenumber>.10
1.2 | subnet - 255.255.255.0
1.3 | gateway - 172.16.<storenumber>.2
1.4 | dsn1 - 172.16.0.43
1.5 | dsn2 - 192.100.100.26
2 | Set Controller IP (>800)
2.1 | ip address - 172.18.<storenumber minus 800>.10 (ex:Store 801 would be 1 (801-800=1)
2.2 | subnet - 255.255.255.0
2.3 | gateway 172.18.<storenumber minus 800>.2 (ex:Store 801 would be 1 (801-800=1)
2.4 | dsn1 - 172.16.0.43
2.5 | dsn2 - 192.100.100.26
3 | Set Primary IP(s)
3.1 | add 1 to last octect of IP address
Modify IE
4 | right click internet explorer icon
4.1 | select proporties
4.2 | select connections
4.3 | select LAN
4.4 | turn proxy on
4.5 | set path to 172.16.0.60
4.6 | set port to 8080
4.7 | select advanced
4.8 | add exception - owa.aerosoles.com/owa
4.9 | select OK to save
5 | Modify Host File
5.1 | start
5.2 | run
5.3 | type c:\windows\system32\drivers\etc press enter
5.4 | edit HOSTS
5.5 | add 65.51.163.2 owa.aereosoles.com to bottom of file (line it up)
5.6 | click X and save changes
6 | Modify Host File
6.1 | Search for email.bat
6.2 | update both files with correct address
6.3 | owa.aerosoles.com/owa (replace ns.aerosoles.com/exchange)

## CONT TESTING
Coalition Store 6 - Register #1 Testing
v2.0
Store Number:
Date of BULK File Build:
Register # 1
Step | Description | Notes | Completed by: | DATE:
1 | Testing
If this is NOT a Windows 7 store, skip to Step 1.2
If this IS a Windows 7 store, and Client does not use Pinpads, skip to Step 1.2
If this IS a Windows 7 store, and Client uses Pinpads, continue to Step 1.1
1.1 | Open hardware and disable pinpads (ONLY to be done when Pinpads are NOT connected at Testing)
In C:\nsb\coalition\dotnet double click on nsb.appbuilder.exe
At the right side double click system design, click on initial layout
highlight custend1 icon(pinpad) and to the right the Misc box it shows the settings
confirm active setting is set to False(Disabled), if set to True(enabled) change to False
confirm sigcap is disabled. Disabled setting is set to False(Disabled), if set to True(Enabled) change to False
to save settings drag toolbox bar over to the right and click on the diskette icon to save
click on the X at upper left corner to close out window
1.2 | Open hardware and disable cashdrawer
1.3 | c:\nsb\coalition\dotnet
1.4 | edit nsb.pos.client.exe.config
1.5 | change cashdrawer1class from opos to virtual
1.6 | Perform SOD - set float as $ client specified
1.7 | Open Register:
1.8 | Unlock POS and select STORE FUNCTIONS, select F1 Start of Day(SOD), select continue
1.9 | You will see prompt online/offline closed registers, if only one register you will see offline closed registers message
1.1 | Select Continue and the EOD/SOD successful message comes up - Start of Day completed, click OK
1.11 | Unlock POS and select STORE FUNCTIONS, Select F7 INITIAL TRAY IN, Before hitting enter to accept tray in make sure the correct register number is populated
1.12 | Hit enter to accept tray in
1.13 | select F2 Open Register, Select F1 Continue
1.14 | Opening Count screen comes up - Key in the beginning Float amount in the actual amount side and hit enter
1.15 | select F8 Continue, receipt will print
REGISTER IS NOW OPEN TO RING SALES
2 | CONFIRM CUST NUMBER IS CORRECT
2.1 | Open SQL Server Management Studio Express from desktop
2.2 | Select Databases, Select MW, Select Tables, scroll down and right click on Parameter_system
2.3 | Select Open table, at right scroll over and look for next_cust_no, click in field to edit and key in
correct cust number if necessary(example store 7 would be 7000001) no leading zero's
store 141 would be 141000001
2.4 | IF THIS IS A HARD DRIVE REPLACEMENT OR AN UPGRADE TO AN EXISTING STORE DO THE FOLLOWING:
2.5 | folllow same directions as above but when keying in the cust number you will need to access
MYSql on your PC, use the following command to look up cust numbers for store:
select num_cp from cust where num_cp like '0016%' order by 1
2.6 | the number in quotes is the 4 digit store number, scroll down and look for the latest cust number
2.7 | when you key in the current cust number add 500 to current number as the cust number
2.8 | IF YOU ARE NOT SURE OF THE ABOVE SEE A SENIOR ANALYST FOR HELP
2.9 | Test Customer database
2.1 | CREATE A CUSTOMER
2.11 | unlock POS and sign into a regular sale, customer search scree will come up
2.12 | Select F2 Create New Customer and type in a fake name, address, phone number
2.13 | Select F1 Accept Customer and select F1 Yes to Save Changes
2.14 | RECALL A CUSTOMER
2.15 | In Customer Search Screen key in the customer you created and select F1 to search and confirm customer info comes up
2.16 | TEST FOR EXISTING CUSTOMER & PURCH HISTORY FROM ANOTHER STORE
2.17 | To retreive an existing customer from another store:
Log into MY SQL on your PC
2.18 | My SQL command to query customer Numbers: select num_cp from cust where num_cp like '0301%' order by 1
2.19 | store number is in the quotation marks, click on the execute button and it should bring up customers for that store
2.2 | unlock POS and sign into a regular sale, customer search scree will come up
2.21 | Key in Cust number in customer number field and select F1 Search
2.22 | should bring up the customer info, click on View/Modify button, select Transactions to bring up the purch history
2.23 | IF CLIENT YOU ARE CONFIGURING FOR HAS PURCHASE HISTORY AND IS NOT COMING UP THEN SEE A SENIOR FOR HELP
3 | If this Client uses Non-Integrated Credit, skip to Step 5
If this Client DOES accept Integrated Credit, continue to Step 3.1
3.1 | Test Credit transaction (Mastercard/Visa)
3.2 | refund above transaction
3.3 | Test Amex transaction
3.4 | refund above transaction
4 | If this Client DOES NOT accept PIN Debit, skip to Step 5
If this Client DOES accept PIN Debit, continue to Step 4.1
4.1 | Test Debit Transaction
4.2 | refund above transaction
5 | If this Client DOES NOT accept Gift Cards, skip to Step 6
If this Client DOES accept Gift, continue to Step 5.1
5.1 | Test Gift transaction
5.2 | refund above transaction
6 | If this Client DOES NOT accept Telecheck Checks, skip to Step 7
If this Client DOES accept Telecheck Checks, continue to Step 6.1
6.1 | Test Check transaction utilizing the Telecheck button on POS
DO NOT USE THE PERSONAL CHECK BUTTON
6.2 | refund above transaction
7 | Test Cash transaction
7.1 | unlock POS and sign into a regular sale, scan an item
7.2 | Key in a sku number from the item file to confirm items are coming up
7.3 | select F8 Total and key in total amount and select F1 Cash
7.4 | Verify tax and tax treshold on transactions (Confirm Rate with Store/Client Contact)
7.5 | Verify printed tax rate matches actual store tax rate, Verify Tax Rate is calculating correctly
7.6 | Confirm Cash Drawer Opens/Closes (If Applicable, and Drawer connected)
7.7 | Post void above Transaction
7.8 | Unlock POS and select Management Functions, select POST VOID, Select Reason Code
7.9 | Key in the original Transaction number and total amount of sale, transaction will come up on screen
7.1 | select F1 YES to reverse(to void out the transaction)
7.11 | PERFORM EOD:
7.12 | Unlock POS and select STORE FUNCTIONS, Select Close Register, Cash Draw will pop Open & Select F1 Continue(If Applicable)
7.13 | Register will prompt to print register totals, select YES to Print, Select NO not to print - this will print to receipt printer
7.14 | You will then be prompted to select F1(OK) to continue with Final Pickup Declaration(MEDIA DECK) - CLICK OK
7.15 | CONFIRM THE STORE NAME, STORE NUMBER ARE ALL CORRECT
7.16 | If all sale transactions were cancelled out there should be no variance, Select F8 Continue
7.17 | You will be prompted to confirm completion - select F1 OK, F2 Cancel - SELECT F1 TO CONTINUE
7.18 | Select F8 End of Day(EOD), Select F1 Continue - End of Day Initiated Banner will appear
7.19 | Once End of Day completes you will See the EOD/SOD Successful prompt come up on screen(Select F1 to continue)
7.2 | Make sure you see the "POLLING SUCCESSFUL" Banner come up on screen(This may take up to 5min)
8 | Pull back/Archive EJ
8.1 | Lock Register and select F5 Inquiry
8.2 | Select F5 EJ
8.3 | Select F5 Execute Query, it should bring up the EJ
8.4 | Select F2 Save Results
8.5 | Key in the filename to be saved, naming convention should be:
8.6 | Client name+Store Number+TestEJ+Page#.txt(EX. Brighton40TestEJ1.txt)
8.7 | In Coalition 6X the EJ is saved by pages, if there is more than one page save all pages
8.8 | file is saved in c:\nsb\coalition\EJRESULTS
8.9 | File Transfer the saved EJ's to T:\POS CONFIG TEAM\INSTALL EJ - 6X\client folder\6 digit store number\
9 | Cash Drawer
9.1 | Open hardware and enable cashdrawer
9.2 | c:\nsb\coalition\dotnet
9.3 | edit nsb.pos.client.exe.config
9.4 | change cashdrawer1class from virtual to opos
10 | Drive Clean up
10.1 | Kill POS
10.2 | Click Stop Services from desltop
10.3 | Open SQL Server Management Studio Express from desktop
10.4 | Go to USICOAL Database and right click on wrkst_local_data
10.5 | Select Open Table - wrkst_local_data
10.6 | Update Next_transaction_no
11 | Data Clean Up (Purge)
11.1 | goto \nsb\coalition\upload
11.2 | delete all files (leave folders)
11.3 | navigate to c:\nsb\coalition\queue
11.4 | delete all files
If this is a Hard-drive Replacement or Conversion, Skip to Step 13.1
If this is a New Store, continue to Step 12
12 | Program the pos keyboard
12.1 | End Coalition
12.2 | Choose Start Menu
12.3 | programs
12.4 | Prewinnprogrammer > Utility > Set to USB > Click Yes and OK for registry entry
12.5 | Choose Start Menu > Programs > Prewinprogrammer > Winprogrammer
12.6 | At top left click on file > Open > click on drop down arrow and select WinProg directory
12.7 | select lay > 133UQ directory > double click on US133UQ.mwf
12.8 | at top left click on file and select update keyboard, USB should already be selected
12.9 | click OK and follow directions, click OK again and keyboard will begin updating
12.1 | once update completes click OK button and click on X at upper right to close out windows
13 | Tasks (FOR WIN XP)
13.1 | Navigate to Tasks
13.2 | Correct store number in proporties if needed
13.3 | Go to Task and Enable TPOLL & REPOLL
14 | CONFIRM STORE NUMBER IS CORRECT IN FIPAYPINCS_CONFIG.XML FILE
14.2 | Click on start and at run prompt type in c:\wansupp
14.3 | double click the fipaypincs_config.xml file and will open in IE
14.4 | At top click on Edit and click"Find on this page"(CTRL+F) in the find box type in"default_store" this will display the 6 digit store #
14.5 | Ask another Installer to confirm the store number and initial below
14.6 | IS STORE NUMBER CORRECT IN FILE?
14.7 | IS STORE NUMBER NOT CORRECT IN FILE?
15 | FOR WINDOWS 7:
15.1 | Open hardware and re-enable pinpads on ALL Registers
15.2 | In c:\nsb\coalition\dotnet double click on nsb.appbuilder.exe
15.3 | At the right side double click system design, click on initial layout
15.4 | highlight custend1 icon(pinpad) and to the right the Misc box it shows the settings
15.5 | confirm active setting is set to True(enabled), if False(disabled) change to True
15.5 | confirm sigcap is active. Active setting is set to True(enabled), if False(disabled) change to True
15.6 | to save settings drag toolbox bar over to the right and click on the diskette icon to save
15.7 | click on the X at upper left corner to close out window
16 | Ip Configuration
16.1 | Set Drive for client specific IP Configuration

## PRIM TESTING
Coalition Store 6 - Addt'l Register Testing
v2.0
Store Number:
Date of BULK File Build:
Step | Description | Notes | REG2: | DATE/TIME | REG3: | DATE/TIME
1 | Open hardware and disable pinpads (ONLY to be done when Pinpads are NOT connected at Testing)
1.1 | In C:\nsb\coalition\dotnet double click on nsb.appbuilder.exe
1.2 | Upper Right corner click on File>Open, select 1-POS and Click OK
1.3 | At the right side double click system design, click on initial layout
1.4 | highlight custend1 icon(pinpad) and to the right the Misc box it shows the settings
1.5 | confirm active setting is set to False(Disabled), if set to True(enabled) change to False
1.6 | confirm sigcap is disabled. Disabled setting is set to False(Disabled), if set to True(Enabled) change to False
1.7 | to save settings drag toolbox bar over to the right and click on the diskette icon to save
1.8 | click on the X at upper left corner to close out window
2 | Testing
2.1 | End coalition
2.2 | Open hardware and disable cashdrawer
2.3 | c:\nsb\coalition\dotnet
2.4 | edit nsb.pos.client.exe.config
2.5 | change cashdrawer1class from opos to virtual
2.6 | Open Register:
2.7 | Unlock POS and select STORE FUNCTIONS, Select F7 INITIAL TRAY IN, Before hitting enter to accept tray in make sure the correct register number is populated
2.8 | Hit enter to accept tray in
2.9 | select F2 Open Register, Select F1 Continue
2.1 | Opening Count screen comes up - Key in the beginning Float amount in the actual amount side and hit enter
2.11 | select F8 Continue, receipt will print
2.12 | REGISTER IS NOW OPEN TO RING SALES
3 | Test Customer database
3.1 | CREATE A CUSTOMER
3.2 | unlock POS and sign into a regular sale, customer search screen will come up
3.3 | Select F2 Create New Customer and type in a fake name, address, phone number
3.4 | Select F1 Accept Customer and select F1 Yes to Save Changes
3.5 | RECALL A CUSTOMER
3.6 | In Customer Search Screen key in the customer you created and select F1 to search and confirm customer info comes up
3.7 | TEST FOR EXISTING CUSTOMER & PURCH HISTORY FROM ANOTHER STORE
3.8 | unlock POS and sign into a regular sale, customer search screen will come up
3.9 | Key in Cust number in customer number field and select F1 Search
3.1 | should bring up the customer info, click on View/Modify button, select Transactions to bring up the purch history(If Applicable)
4 | If this Client uses Non-Integrated Credit, skip to Step 6
If this Client DOES accept Integrated Credit, continue to Step 4.1
4.1 | Test Credit transaction (Mastercard/Visa)
4.2 | refund above transaction
4.3 | Test Amex transaction
4.4 | refund above transaction
5 | If this Client DOES NOT accept PIN Debit, skip to Step 6
If this Client DOES accept PIN Debit, continue to Step 5.1
5.1 | Test Debit Transaction
5.2 | refund above transaction
6 | If this Client DOES NOT accept Gift Cards, skip to Step 7
If this Client DOES accept Gift, continue to Step 6.1
6.1 | Test Gift transaction
6.2 | refund above transaction
7 | If this Client DOES NOT accept Checks, skip to Step 8
If this Client DOES accept Checks continue to Step 7.1
7.1 | Test Check transaction
7.2 | refund above transaction
8 | Test Cash transaction
8.1 | unlock POS and sign into a regular sale, scan an item
8.2 | Key in a sku number from the item file to confirm items are coming up
8.3 | select F8 Total and key in total amount and select F1 Cash
8.4 | Verify tax and tax treshold on transactions (Confirm Rate with Store/Client Contact)
8.5 | Verify printed tax rate matches actual store tax rate, Verify Tax Rate is calculating correctly
8.6 | Confirm Cash Drawer Opens/Closes (If Applicable, and Drawer connected)
8.7 | Post void above Transaction
8.8 | Unlock POS and select Management Functions, select POST VOID, Select Reason Code
8.9 | Key in the original Transaction number and total amount of sale, transaction will come up on screen
8.1 | select F1 YES to reverse(to void out the transaction)
8.11 | CLOSE REGISTER:
8.12 | Unlock POS and select STORE FUNCTIONS, Select Close Register, Cash Draw will pop Open & Select F1 Continue(If Applicable)
8.13 | Register will prompt to print register totals, select YES to Print, Select NO not to print - this will print to receipt printer
8.14 | You will then be prompted to select F1(OK) to continue with Final Pickup Declaration(MEDIA DECK) - CLICK OK
8.15 | CONFIRM THE STORE NAME, STORE NUMBER ARE ALL CORRECT
8.16 | If all sale transactions were cancelled out there should be no variance, Select F8 Continue
8.17 | You will be prompted to confirm completion - select F1 OK, F2 Cancel - SELECT F1 TO CONTINUE
9 | Open hardware and enable cashdrawer
9.1 | c:\nsb\coalition\dotnet
9.2 | edit nsb.pos.client.exe.config
9.3 | change cashdrawer1class from virtual to opos
10 | Drive Clean up
10.1 | Kill POS
10.2 | Click Stop Services from desltop
10.3 | Open SQL Server Management Studio Express from desktop
10.4 | Go to USICOAL Database and right click on wrkst_local_data
10.5 | Select Open Table - wrkst_local_data
10.6 | Update Next_transaction_no
11 | Program the pos keyboard
11.1 | End Coalition
11.2 | Choose Start Menu
11.3 | programs
11.4 | Prewinnprogrammer > Utility > Set to USB > Click Yes and OK for registry entry
11.5 | Choose Start Menu > Programs > Prewinprogrammer > Winprogrammer
11.6 | At top left click on file > Open > click on drop down arrow and select WinProg directory
11.7 | select lay > 133UQ directory > double click on US133UQ.mwf
11.8 | at top left click on file and select update keyboard, USB should already be selected
11.9 | click OK and follow directions, click OK again and keyboard will begin updating
11.1 | once update completes click OK button and click on X at upper right to close out windows
12 | Tasks (FOR WIN XP)
12.1 | Navigate to Tasks
12.2 | Correct store number in proporties if needed
13 | CONFIRM STORE NUMBER IS CORRECT IN FIPAYPINCS_CONFIG.XML FILE
13.1 | Click on start and at run prompt type in c:\wansupp
13.2 | double click the fipaypincs_config.xml file and will open in IE
13.3 | At top click on Edit and click"Find on this page"(CTRL+F) in the find box type in"default_store" this will display the 6 digit store #
13.4 | Ask another Installer to confirm the store number and initial below
13.5 | IS STORE NUMBER CORRECT IN FILE?
13.6 | IS STORE NUMBER NOT CORRECT IN FILE?
14 | For Win7 Only:
14.1 | Open hardware and Re-Enable the pinpads (ONLY to be done when Pinpads are NOT connected at Testing)
14.2 | In C:\nsb\coalition\dotnet double click on nsb.appbuilder.exe
14.3 | Upper Right corner click on File>Open, select 1-POS and Click OK
14.4 | At the right side double click system design, click on initial layout
14.5 | highlight custend1 icon(pinpad) and to the right the Misc box it shows the settings
14.6 | confirm active setting is set to False(Disabled), if set to True(enabled) change to False
14.7 | confirm sigcap is disabled. Disabled setting is set to False(Disabled) - If set to True(Enabled), change to False
14.8 | to save settings drag toolbox bar over to the right and click on the diskette icon to save
14.9 | click on the X at upper left corner to close out window
15 | IP Configuration
15.1 | Set Drive for client specific IP Configuration

## GO LIVE
Coalition Store 6 - Go Live Checklist
v2.0
STEPS MUST BE COMPLETED AS LISTED - THE NUMBERS AND LETTERS ARE NOT ARBITRARY
Store #:
Phone Number:
Date of Go-Live:
Verify Time Zone was set properly!!!!
Step | Description | REG1: | DATE/TIME | REG2: | DATE/TIME | REG3: | DATE/TIME | NOTES (Examples: Hardware unavailable, Hardware failure, Card-Type not Available, etc.)
1 | Assigning yourself to the Install Ticket you are Installing for
1.1 | Click on Edit to edit the Install Ticket you are Installing for
1.2 | Change the Status of the ticket to Installing - when you begin, Post Install - a Not completed Installl, Closed - When Install is completed
1.3 | go to Assignees & Notifications section at bottom of ticket
1.4 | Highlight your name in the workspace members box
1.5 | click on the arrow to put your name in the assignees box
1.6 | click Save
1.7 | ***CONFIRM CORRECT BUILD & PLATFORM IS ON DRIVE BEFORE BEGINNING INSTALL***
1.8 | Check the Install ticket for whats listed that the store is suppose to have and if not sure
1.9 | confirm with purchasing dept and compare with whats on drive
1.1 | CONFIRM THE CORRECT PLATFORM(XP, WIN7) BY GOING TO PROPERTIES OF MY COMPUTER
1.11 | Confirm correct build by going to C:\, IF XL2 Drivers folder = XL2 build
1.12 | IF 7000AIO Drivers folder = TP7 AIO BUILD
To differ between a TP7K Full & TP7K AIO Image Build is to look in regedit: HKEY_Local_Machine>Software>OLEforRetail>Line Display
If you do not see a VF35 folder then it’s a TP7K Full Image, if the VF35 folder is there then its TP7K AIO image
1.13 | KEY IN HERE WHAT TYPE OF PLATFORM & BUILD IS THIS:
2 | Change the POS Printer (if needed)
2.1 | NOTATE TYPE OF PRINTER INSTALLED: TM6000(DT50) Printer (has MICR to ensorse checks) or TM88 (No MICR)
(Check Install Ticket/EOF to confirm type of receipt printer store is using matches EOF)
2.2 | Choose Start Menu
2.3 | programs
2.4 | Opos
2.5 | opossetup
2.6 | click + by Device
2.7 | Click + by Printer
2.8 | right mouse click printer and delete
2.9 | right click POS Printer
2.1 | click add printer
2.11 | Choose correct printer (TMH6000XX)
2.12 | Add NSBOPOSPRINTER in name field
2.13 | click next
2.14 | choose Com3
2.15 | Select check health
3 | Change the MICR (if needed)
3.1 | from opossetup
3.2 | click + by MICR
3.3 | right click and choose delete
3.4 | right click and choose add MICR
3.5 | Choose MICR type (TMH6000XX)
3.6 | Add NSBOPOSMICR in name field
3.7 | Click next
3.8 | Select COM3
3.9 | select OK to use
3.1 | Finish
4 | CONFIRM DATE/TIME/TIMEZONE IS CORRECT
4.1 | Click on start>control panel, select date & time and confirm the date & time/ timezone is all correct, make changes if necessary
5 | CONFIRM MODEL & TYPE OF PINPADS
5.1 | DOES STORE HAVE PINPADS?
5.2 | Notate Pinpad Model (Example: I6580, I6780, I3070)
5.3 | Notate Type of Pinpad (Example: Titan = Black, Standard= Gray)
Have onsite contavt look at the back of the Pinpad - Model Type is located under serial number and where it says model#
5.4 | YOU MUST UPDATE THE INSTALL TICKET/INSTALL CONFIRMATION EMAIL WITH THE MODEL & TYPE OF PINPAD
6 | ****CONFIRM POST INSTALL RC PACKAGES ARE INSTALLED; THIS IS DONE ON THE CONTROLLER ONLY****
6.1 | Use the following link for instructions on confirming ALL RC Post Install Packages are installed:
6.2 | Post-Install Bundle General Overview
6.3 | If any RC packages are not installed they need to be installed
6.4 | NOTATE HERE ANY RC PACKAGES NOT INSTALLED:
6.5 | NOTATE HERE WHAT RC PACKAGES WERE INSTALLED:
7 | CONFIRM CUST NUMBER IS CORRECT
7.1 | Open SQL Server Management Studio Express from desktop
7.2 | Select Databases, Select MW, Select Tables, scroll down and right click on Parameter_system
7.3 | Select Open table, at right scroll over and look for next_cust_no, click in field to edit and key in
7.4 | correct cust number if necessary(example store 7 would be 7000001) no leading zero's
store 141 would be 141000001
7.5 | NOTATE THE CUSTOMER NUMBER HERE:
7.6 | IF THIS IS A HARD DRIVE REPLACEMENT DO THE FOLLOWING:
7.7 | folllow same directions as above but when keying in the cust number you will need to access
MYSql on your PC, use the following command to look up cust numbers for store:
7.8 | select num_cp from cust where num_cp like '0016%' order by 1
7.9 | the number in quotes is the 4 digit store number, scroll down and look for the latest cust number
7.1 | when you key in the current cust number add 500 to current number as the cust number
7.11 | IF YOU ARE NOT SURE OF THE ABOVE SEE A SENIOR ANALYST FOR HELP
8 | AJB(FIPAY)
8.0.1 | CONFIRM CORRECT AJB BUILD IS INSTALLED
8.0.2 | New stores: AJB 20394
8.0.3 | Drive Replacements at 1-Reg stores: AJB 20394
8.0.4 | Drive Replacements at Multi-Reg store: Match “good” register and install for that AJB Build
8.0.5 | Exceptions would be for: 7FAM, Bribor, Brighton, Equinox, Lucy, QVC
CONFIRM STORE NUMBER IS CORRECT IN FIPAYPINCS_CONFIG.XML FILE
8.1 | Click on start and at run prompt type in c:\wansupp
8.2 | double click the fipaypincs_config.xml file and will open in IE
8.3 | At top click on Edit and click"Find on this page"(CTRL+F) in the find box type in "default_store" this will display the 6 digit store #
8.4 | Ask another Installer to confirm the store number initial where appropriate below
8.5 | IS STORE NUMBER CORRECT IN FILE?
8.6 | IS STORE NUMBER NOT CORRECT IN FILE?
9 | UPDATE NAV (VIA INTERNET CONNECTION)
9.1 | Double click on the NAV Shield at bottom right in system tray
9.2 | click on update, NAV Definitions should download and update
If this is a New Store, skip to Step 12.1
If this is a Hard-drive Replacement or Conversion, continue to Step 10.1
10 | Drive Clean up
10.1 | Confirm that ALL xml's in ALL registers have the SAME Merchant #
10.2 | Kill POS
10.3 | Click Stop Services from desktop
10.4 | Open SQL Server Management Studio Express from desktop
10.5 | Go to USICOAL Database and right click on wrkst_local_data
10.6 | Select Open Table - wrkst_local_data
10.7 | Update Next_transaction_no (Please utilize "Last Trans" process to determine Next_transaction_no)
11 | Program the pos keyboard
11.1 | End Coalition
11.2 | Choose Start Menu
11.3 | programs
11.4 | Prewinnprogrammer > Utility > Set to USB > Click Yes and OK for registry entry
11.5 | Choose Start Menu > Programs > Prewinprogrammer > Winprogrammer
11.6 | At top left click on file > Open > click on drop down arrow and select WinProg directory
11.7 | select lay > 133UQ directory > double click on US133UQ.mwf
11.8 | at top left click on file and select update keyboard, USB should already be selected
11.9 | click OK and follow directions, click OK again and keyboard will begin updating
11.1 | once update completes click OK button and click on X at upper right to close out windows
12 | Check for if Master zip files have been updated since config
12.1 | Got to T:\StoreSystemsDevelopment\philstuff\production\ client folder and check if files have been
updated since time of config, if so need to download and copy in the updated master files
12.2 | NOTATE HERE IF FILES HAVE BEEN UPDATED SINCE CONFIG YES/NO?
13 | Incremental Files
13.1 | build, transmit and procees any needed incremental files
13.2 | AFTER ALL FILES HAVE FINISHED PROCESSING, REPROCESS THE FOLLOWING FILES IN ORDER ONLY IF THERE
ARE CLIENT SPECIFIC NON_MERCH FILES:
13.3 | 1. KWI_NONMERCH, 2. CLIENT SPECIFIC NON_MERCH FILES, 3. ZIPTAX
14 | Symbol MC3000 (not all clients)
14.1 | Exit app on handheld
14.2 | double click to start
14.3 | select configure
14.4 | select dowload TIP driver
14.5 | after success
14.6 | choose OK, back then back
14.7 | From Explorer
14.8 | navigate to my mobile device
14.9 | copy TIP driver
14.1 | navigate to the symbol device
14.11 | copy the driver into the Application folder
15 | Delete and Install Local/Network Printers
15.1 | Printers and faxes
15.2 | delete all printers except MS doc writer
15.3 | Install new printer
15.4 | confirm with person onsite if the printer is attached to Reg 1 or if its going to be networked(Ethernet/CAT5 Cable)
15.5 | If local(Attached to Reg 1)USB Connection, store should have printer software CD and install with CD
15.6 | if no printer cd is onsite download printer driver from website or see if driver software is in T:\POS CONFIG TEAM\Printer drivers
15.7 | If networked, confirm printer is on network - try to ping network printer IP from dos prompt on register
15.8 | click on start, click on run - at run prompt type in cmd and hit enter, this will take you to the dos prompt window
If this is a New Store, skip to Step 22 (Testing)
If this is a CONTROLLER Hard-drive Replacement, continue to Step 16.1
16 | Resetting Replication Manager
16.1 | Stop services on all Primary registers
16.2 | run resetreplication.bat (c:\resetreplication.bat) on all Primary registers
16.3 | re-boot all registers
16.4 | log into replication manager on register #1 after it is up and verify you can see all registers
16.5 | pos load may fail on primary register(s) until replication has been updated
17 | Pin Pads
17.1 | Pin Pads in new stores are most likely Powered USB Connection
17.2 | If you need to change the port setting from usb to serial and vise versa in the Pinpad, see document in
T:\POS CONFIG TEAM\Installs Troubelshooting\Pinpads\changing port settings on the Ingenico 6780
Claim & Delete Forms
17.3 | Go To c:\Ing6780, select Opos Test App18.exe
Prompt will come up to "CHOOSE DEVICE" Click on OK
17.4 | Click on the 'FORM' TAB at top, click on Open button, click Claim button, the claim status
17.5 | should change to 'Claimed", if not then the register is not communicating with PINPAD
17.6 | Click Enable button, Click Delete Ads
17.7 | Wait a minute, click on reset unit to reboot pinad, cancel out of the application
6X SINGLE REGISTER DEBIT FIX - THIS NEEDS TO BE DONE ON ALL REGISTERS
THIS IS FOR PINPAD & NON-PINPAD CLIENTS
17.8 | End Coalition program
17.9 | File transfer singleregisterdebitfix6X from Post Install\6X SINGLE REGISTER DEBIT FIX - DO NOT REMOVE
to c:\nsb\coalition\download directory
17.1 | follow install instructions, this runs the forms for the pinpad, fixes for ajb.dll's and will reboot the register
18 | Programming Register Scanner
18.1 | confirm with tech the model type of scanner that is onsite, model type is on the scanner
18.2 | click on below link and select programming barcodes document for scanner
18.3 | http://kwiki.kligerweiss.net/helpdesk/tiki-index.php?page=POS+Scanner+Scan+Sheets+and+Client+Specific+Sheets
18.4 | file transfer and print out document and have tech scan barcodes
19 | Touch Screen Calibration
19.1 | Open ELO Icon from taskbar at bottom right
19.2 | click on ELO Icon and select Align, a bullseye target will come up, have tech depress target with thumb
19.3 | then let go, target will move to bottom of screen and depress with thumb again and let go
19.4 | target will move again and depress and let go, you will see a green checkmark box
19.5 | click on the green checkmark box to complete calibration
Test Touchscreen
19.6 | Confirm touch screen is working
19.7 | have store using touch depress a function key on the screen in coalition to confirm touch is working
20 | END COALITION AND RUN CHANGE DATE FORMAT ON ALL REGISTERS
21 | CHANGE DATE FORMAT - DONE ON ALL REGISTERS
21.1 | go into control panel and select Regional & Language Options, click on customize button
21.2 | click on Date tab at top, change short date format to M/D/YY, click on Apply & OK Buttons
21.3 | this will fix the issue when scanning home store returns
21.4 | RESTART COALITION
21.5 | Run Gift Card Fix
21.6 | File Transfer to C:\ the gcfix file from T:\POS CONFIG TEAM\GIFT CARD FIX - 6X Only
21.7 | open up windows explorer, go to C:\ and Double click on gcfix file to execute
22 | Testing
22.1 | Open Register:
22.2 | Unlock POS and select STORE FUNCTIONS, select F1 Start of Day(SOD), select continue
22.3 | You will see prompt online/offline closed registers, if only one register you will see offline closed registers message
22.4 | Select Continue and the EOD/SOD successful message comes up - Start of Day completed, click OK
22.5 | select F2 Open Register, Select F1 Continue
22.6 | cash draw should pop open if not check connections and confirm in c:\nsb\coalition\dotnet\
edit nsb.pos.client.exe.config and confirm cashdrawer1class is set to OPOS(enabled) VIRTUAL(Disabled)
22.7 | Opening Count screen comes up - Key in the beginning Float amount in the actual amount side and hit enter
22.8 | Confirm amount with store(if applicable)
22.9 | select F8 Continue, receipt will print
22.1 | REGISTER IS NOW OPEN TO RING SALES
If this Client uses Non-Integrated Credit, skip to Step 25
If this Client DOES accept Integrated Credit, continue to Step 23.1
23.1 | TEST CREDIT CARD TRANSACTION(Mastercard/Visa)
23.2 | Unlock and sign onto register
23.3 | select F6 Non Merch
23.4 | select F2 Shipping, key in .01 for shipping amount, hit enter
23.5 | select F8 Total
23.6 | select CREDIT for credit auth
23.7 | Have person swipe there card on keyboard with mag strip away from them
23.8 | They will then be prompted to sign, person will sign there name on pinpad and hit accept( if applicable)
23.9 | on register screen you will see there signature, click on Continue to complete the transaction
23.1 | CONFIRM ADDRESS & PHONE NUMBER ARE CORRECT ON RECEIPT
23.11 | REFUND ABOVE TRANSACTION
23.12 | Unlock and sign onto register
23.13 | select F3 Return, you will be prompted does this return have original receipt
23.14 | Home store return is with receipt, return without a receipt is without
23.15 | select F1 Yes, have store scan bottom of receipt, transaction info should populate and come up
on screen, if not manually key in the store number, register number, transaction number, date of sale
23.16 | select F3 return item, select reason code and click F1 OK, select F1 Finished
you will be brought back into sales transaction screen, select F8 Total
23.17 | Key in the amount and select CREDIT, have person swipe there credit card on keyboard
23.18 | They will then be prompted to sign, person will sign there name on pinpad and hit accept( if applicable)
23.19 | on register screen you will see there signature, click on Continue to complete the return
23.2 | if they do not see prompt to sign on the pinpad then pinpad might be disabled in Appbuilder
23.21 | Test Amex transaction
23.22 | repeat above steps to test AMEX Card(if they have onsite)
24 | If this Client DOES NOT accept PIN Debit, skip to Step 25
If this Client DOES accept PIN Debit, continue to Step 24.1
24.1 | TEST DEBIT TRANSACTION
24.2 | Unlock and sign onto register
24.3 | select F6 Non Merch
24.4 | select F2 Shipping, key in .01 for shipping amount, hit enter
24.5 | select F8 Total
24.6 | select F3 Debit (Make sure the person has there debit card and are ready to swipe before selecting F3 Debit)
24.7 | have person swipe debit card on pinpad and follow prompts
24.8 | REFUND ABOVE TRANSACTION
24.9 | Unlock and sign onto register
24.1 | select F3 Return, you will be prompted does this return have original receipt
24.11 | Home store return is with receipt, return without a receipt is without
24.12 | select F1 Yes, have store scan bottom of receipt, transaction info should populate and come up
24.13 | on screen, if not manually key in the store number, register number, transaction number, date of sale
24.14 | select F3 return item, select reason code and click F1 OK, select F1 Finished
24.15 | you will be brought back into sales transaction screen, select F8 Total
24.16 | ***For testing purposes you will return money back on debit card using credit auth Tender***
24.17 | Key in the amount and select CREDIT, have person swipe there card on keyboard
24.18 | They will then be prompted to sign, person will sign there name on pinpad and hit accept
24.19 | on register screen you will see there signature, click on Continue to complete the return
25 | If this Client DOES NOT accept Gift Cards, skip to Step 26
If this Client DOES accept Gift, continue to Step 25.1
25.1 | TEST GIFT CARD ISSUE(SALE) & REDEEM TRANSACTION
25.2 | GIFT CARD ISSUE(SALE):
25.3 | unlock POS and sign into a regular sale
25.4 | select NON MERCH, SELECT GIFT CARD, Have store swipe gift card, key in $5.00 for the amount
25.5 | Select Total and key in amount $5.00 and select cash for tender
25.6 | GIFT CARD REDEEM:
25.7 | redeem gift card by going back into a regular sale, select NON MERCH
25.8 | Select Shipping, key in $5.00 hit enter, select F8 Total
25.9 | key in $5.00 and select Gift Card as Tender to redeem
25.1 | have store swipe same gift card that was issued
*******IF STORE DOES NOT HAVE ANY GIFT CARDS ONSITE NOTE THAT IN THE INSTALL TICKET******
25.11 | IF GIFT CARD SALE/REDEEM WAS PERFORMED, CANCEL OUT THE $5 CASH TRANSACTION:
25.12 | Unlock POS and sign into a regular sale
25.13 | select F3 Return, you will be prompted does this return have original receipt
25.14 | Home store return is with receipt, return without a receipt is without
25.15 | select F1 Yes, have store scan the previous receipt - the one with shipping, transaction info should populate and come up on screen, if not manually key in the store number, register number, transaction number, date of sale
25.16 | select F3 return item, select reason code and click F1 OK, select F1 Finished
25.17 | you will be brought back into sales transaction screen, select F8 Total
25.18 | key in $5.00 and select Cash
26 | If this Client DOES NOT accept Checks, skip to Step 27
If this Client DOES accept Checks continue to Step 26.1
26.1 | Test Check transaction
26.2 | Unlock POS and sign into a regular sale, select NON-Merch, Select Shipping, key in $10.00 for the amount and hit enter
26.3 | select F8 Total, select More Tenders, key in $10.00 and select Check
26.4 | Store inserts check and should authorize, if check auth does not go through, check the system day log in c:\wansupp\logs for the error
26.5 | Post Void the Check transaction
26.6 | Unlock POS and select Management Functions, select POST VOID, Select Reason Code
26.7 | Key in the original Transaction number and total amount of sale, transaction will come up on screen
26.8 | select F1 YES to reverse(to void out the transaction)
27 | Test Cash transaction
27.1 | unlock POS and sign into a regular sale, scan an item
27.2 | if no product is onsite you must key in a sku number from the item file to confirm items are coming up
27.3 | select F8 Total and key in total amount and select F1 Cash
27.4 | Verify tax and tax treshold on transactions are calculationg correctly(Confirm TAX Rate with Store/Client Contact)
27.5 | Verify printed tax rate matches actual store tax rate
27.7 | Confirm Cash Drawer Opens/Closes (If Applicable, and Drawer connected)
27.8 | Post void above Transaction
27.9 | Unlock POS and select Management Functions, select POST VOID, Select Reason Code
27.1 | Key in the original Transaction number and total amount of sale, transaction will come up on screen
27.11 | select F1 YES to reverse(to void out the transaction)
27.12 | PERFORM EOD ***IF CLIENT IS ALSO INSTALLING MPOS YOU NEED TO COMPLETE TESTING MPOS BEFORE RUNNING EOD***
27.13 | Unlock POS and select STORE FUNCTIONS, Select Close Register, Cash Draw will pop Open & Select F1 Continue
27.14 | Register will prompt to print register totals, select YES to Printer, Select NO not to print - this will print to receipt printer
27.15 | You will then be prompted to select F1(OK) to continue with Final Pickup Declaration(MEDIA DECK) - CLICK OK
27.16 | CONFIRM THE STORE NAME, STORE NUMBER ARE ALL CORRECT
27.17 | If all sale transactions were cancelled out there should be no variance, if you did a Gift card sale and selected cash you
need to key in the cash amount in the ACT.AMT side & select F8 Continue
27.18 | You will be prompted to confirm completion - select F1 OK, F2 Cancel - SELECT F1 TO CONTINUE
27.19 | Select F8 End of Day(EOD), Select F1 Continue - End of Day Initiated Banner will appear
27.2 | Once End of Day completes you will See the EOD/SOD Successful prompt come up on screen(Select F1 to continue)
27.21 | Make sure you see the "POLLING SUCCESSFUL" Banner come up on screen(This may take up to 5min)
28 | Data Clean Up (Purge)
28.1 | At Desktop Stop NSB Services
28.2 | goto \nsb\coalition\upload
28.3 | delete all files (leave folders)
28.4 | navigate to c:\nsb\coalition\queue and delete all files
28.5 | At Desktop Restart NSB Services
29 | Pull back/Archive EJ
29.1 | Lock Register and select F5 Inquiry
29.2 | Select F5 EJ
29.3 | Select F5 Execute Query, it should bring up the EJ
29.4 | Select F2 Save Results
29.5 | Key in the filename to be saved, naming convention should be:
29.6 | Client name+Store Number+InstallEJ+Page#.txt(EX. Brighton40InstallEJ1.txt)
29.7 | Select All Items
29.8 | In Coalition 6X the EJ is saved by pages, if there is more than one page save all pages
29.9 | file is saved in c:\nsb\coalition\EJRESULTS
29.1 | File Transfer the saved EJ's to T:\POS CONFIG TEAM\INSTALL EJ - 6X\client folder\6 digit store number
30 | Set Live Store Number
30.1 | SET STORE LIVE
30.2 | navigate to c:/nsb/coalition/file
30.3 | Edit logpas.bat
30.4 | CHANGE STORE NUMBER TO THE 6 DIGIT STORE # YOU ARE INSTALLING FOR
CONFIRM SETTINGS FOR CHARGESEND IN LOGPAS ARE SETUP
30.5 | CONFIRM THE FIELDS CONTAINING BACKOFFICE ARE SETUP WITH CLIENT SPECIFIC INFO
30.6 | IF YOU DO NOT SEE THE FIELDS CONTAINING BACKOFFICE THEN THIS WAS NOT DONE AT CONFIG AND NEEDS TO BE COMPLETED
30.7 | New Logpas file is located in:
30.8 | T:\POS CONFIG TEAM\Installation Documents and Electronic Tracking-12-23-10\Coalition 6\Production Documents and Required Files\Post Install\All OS-Global\Logpas
30.9 | Follow the readme instructions if this was not done at config
30.1 | Save changes & Exit
30.11 | STOP & START THE KWITCP SERVICE
Verify that KWI_TCP_Service log file (located in NSB\Coalition\Logs) is running with the correct store number (i.e. 106089.2013.06.05.KWITCP.log not 999999.2013.06.05.KWITCP.log)
31 | CHECK/CONFIRM THE FIPAY FILE IS REMOVED FROM STORE INSTALL FOLDER
31.1 | Delete any fipay files in STORE INSTALL FOLDER you are installing for
32 | UPDATE INSTALL TICKET & PROJECT VITALS TAB WITH STORE PH# & PUBLIC IP ADDRESS
32.1 | UPDATE INSTALL TICKET IN DETAIL WITH ALL INFORMATION THAT WAS DONE DURING INSTALL
33 | Archive Internal IP Info on POS
33.1 | click on start, click on run, at run prompt type in cmd to get to a dos prompt
33.2 | type in ipconfig /all, hold down ALT+Printscreen buttons to copy screen
33.3 | Open a word document, right click in document and left click paste
33.4 | naming convention to save document as: 6 digit store number+Reg1IPInfo.txt, EX. 218141Reg1IPInfo.txt
33.5 | Save to T:\POS CONFIG TEAM\Stores Internal IP
34 | Updates
34.1 | See Post Install Tab
If this Client DOES NOT utilize KWI Cloud 9 Mobile, skip to Step 46
If this Client DOES utilize KWI Cloud 9 Mobile, continue to Step 35
35 | Cloud 9 Mobile
35.1 | Direct store through mPOS Client Installation Instructions document (included with each mPOS shipment)
35.2 | Confirm the devices connect to the SSID from the mPOS IP Sheet (found in the POS Install Ticket) - Via Settings > WiFi > Connecting to correct SSID
35.3 | Dial into Register 1 and ping each device (each mPOS unit, and each Printer).
35.4 | Confirm store can do a Manual Sync on the devices : From Login Page > mPOS Settings > Pasword is 1234 > Scroll to bottom >Sync button
If this Client DOES NOT utilize KWI Cloud 9 Mobile Inventory, skip to Step 37
If this Client DOES utilize KWI Cloud 9 Mobile Inventory, continue to Step 36
36 | Cloud 9 Mobile (Inventory) - PLEASE ENSURE DEVICE IS IN TRAINING MODE!!!!
36.1 | Log into mPOS app and select Inventory Management
36.2 | Select Transfers Out
36.3 | Select To Store from drop down menu and touch Start
36.4 | Scan all items
36.5 | Touch BOOK, Touch YES to book the Transfer Out
36.6 | Touch the home button at top of screen to exit out of Transfer Out Screen
If this Client DOES NOT utilize KWI Cloud 9 Mobile Sales, skip to Step 46
If this Client DOES utilize KWI Cloud 9 Mobile Sales, continue to Step 37
37 | Cloud 9 Mobile (Sales)
38 | Confirm Start Of Day on the POS has been performed before testing the mPOS
***If the mPOS devices were config'd with a cash draw then tray association should be done already***
If Client is on 4.x and has a cash drawer, comtimue to step 38.1
If Client is on 4.x and does not have a cash drawer skip to step 39
If Client is on 3.x, skip to step 39
38.1 | Tray In:
38.2 | from mPOS app select Store Operations and login
38.3 | Select TRAY IN, Scan Barcode on Cash Draw and cash drawer should pop open (THIS IS PERFORMED ONLY ON 1 MPOS DEVICE)
38.4 | mPOS device will prompt to key in float amount, key in float amount
38.5 | mPOS device will prompt Start of Day, select submit button to accept
38.6 | go back into mPOS app and select POS
39 | Credit Card Transaction:
39.1 | Confirm successful login using Store Associate credentials
39.2 | Scan an Item (Confirm UPC Scanner shoots a laser and scans barcode)
39.3 | Confirm SKU is read, and populates into the transaction
39.4 | Price Modify the item: Item > Item Discount $ > Other > enter $ amount to reduce to $0.01
39.5 | Select Total, Checkout, select Credit Card, Swipe a Credit Card through the MSR; Confirm the numbers populate
39.6 | Confirm successful Credit Authorization
39.7 | PRINT RECEIPT
40 | Return Above Transaction:
40.1 | login into the POS application
40.2 | select transaction at the bottom and select return with a receipt
40.3 | scan receipt, transaction info should populate, select reason code for return
40.4 | select done, total, checkout, swipe card through MSR and print receipt
41 | Gift Card Issue:
41.1 | sign back into POS Application and select Transaction button at bottom of screen
41.2 | select Issue Gift Card, Key in $5.00 for the amount and swipe card or manually enter the gift card account number
41.3 | If Tax has been added to the total amount, - skip to
41.4 | select transaction button at bottom of screen and select Add Transaction Tax
41.5 | select done, key in the number ZERO for the tax exempt code and touch OK
41.6 | Select Total, Checkout, select Cash, scan barcode on cash draw, key in the amount $5.00
41.7 | Touch CHARGE Button and cash draw will open
41.8 | ON SPLIT TENDERS, THE CASH DRAW OPENS AFTER ALL TENDERS HAVE BEEN INPUTED
42 | Gift Card Redeem:
42.1 | login into the POS application
42.2 | Scan an Item (Confirm UPC Scanner shoots a laser and scans barcode)
42.3 | Confirm SKU is read, and populates into the transaction
42.4 | Price Modify the item: Item > Item Discount $ > Other > enter $ amount to reduce to $5.00
42.5 | Select Total, Checkout, select Gift Card, key in the amount $5.00 and swipe the Gift Card
42.6 | PRINT RECEIPT
43 | Return/cancel out the $5.00 cash transaction
43.1 | sign back into POS Application
43.2 | select transaction at the bottom and select return with a receipt
43.3 | scan Gift Card Redeem Receipt, transaction info should populate, select reason code for return
43.4 | Select Total, Checkout, select Cash, scan barcode on cash draw, key in the amount $5.00
43.5 | Touch CHARGE Button and cash draw will open
44 | Confirm all info on receipt is correct
44.1 | Confirm Store Name/Store #/Store Address is correct on receipt
44.2 | Confirm Logo is correct on receipt
44.3 | Confirm Tax Rate is correct on receipt (This should be confirmed with Client/Store Contact)
44.4 | Confirm Return Policy is correct
44.5 | EMAIL a receipt (to Onsite Contact):
If this Client DOES NOT utilize KWI Cloud 9 Mobile Clienteling, skip to Step 32
If this Client DOES utilize KWI Cloud 9 Mobile Clienteling, continue to Step 32a
ENABLE VNC 2 FACTOR AUTHENTICATION- ***ONLY FOR BRAND NEW CLIENTS***
From the System Tray of the Windows Tool bar right click the VNC Icon and left click ADMIN PROPERTIES
•To enable the handshake, verify the Display Query Window Default action is set to Refuse and 30 Seconds
For Detailed description of setting VNC to 2 Factor use the link below:
http://kwiki.kligerweiss.net/helpdesk/tiki-index.php?page=Ultra+VNC+Installation+and+Support+for+Posready+2009+Posready7+or+Multiple+Software+Platforms#Ultra_VNC_Admin_and_2-Factor_Authentication_Hangup_Properties
45 | Cloud 9 Mobile (Clienteling) *Requires Sales License*
45.1 | Not implemented at KWI (as of 4/10/13)
46 | QAS Updates
(Tahari /Dooney)
46.1 | QAS update must be sent the night of Install. Please alert Jim McMahon (jmcmahon@kwi.com)
47 | Alert Data Team to Set for Polling - FOR DATA TEAM USE ONLY
47.1 | Send Install Completion email to Data Team, InstallGroup, DriveInstallGroup
47.2 | Verify KWI CALL TABLE - Polling Number is set to correct IPx Number
47.3 | Set up 'do' Csi\l - Setup in stores table
47.4 | Set up store for incremental CUST/ITEM Download
47.5 | Attach the CONFIG\INSTALL CHECKLIST TO INSTALL TICKET

## POST INSTALLS
Coalition Store 6 - Post Install
v2.0
Store #:
Phone Number:
Date of Go-Live:
Step | Description | Notes | Completed by: | Date/Time
Must be Installed after updating Logpas. If You DO Install before updating Logpas, you will be required to stop and start the KWITCP services via running net stop kwitcp & net start kwitcp. If you do not perform this step, the KWITCP service will be running with the store number 999999. Failure to do this can cause various file transfer issues until the KWITCP service is restarted or the register is rebooted.
1 | Root Cause/SSD Updates
1.1 | Navigate to T:\POS CONFIG TEAM\Installation Documents and Electronic Tracking-12-23-10\Coalition 6\Production Documents and Required Files\Post Install
1.2 | Transfer ALL Updates (RC_v6001, RC_v6002, RC_v6003, Credit Certs ALL Registers,All OS-Global, AJB, etc.) to c:\nsb\coalition\download (ONE AT A TIME, IN ORDER)
1.3 | process above transferred update
1.4 | repeat steps 1 and 1a for any additional updates
2 | Client Specific Updates
2.1 | Navigate to T:\POS CONFIG TEAM\Installation Documents and Electronic Tracking-12-23-10\Coalition 6\Production Documents and Required Files\Post Install\Client Specific Updates-SSD
2.2 | Open CLIENT SPECIFIC folder and install updates
2.3 | If a folder DOES NOT exist for the client there are no files to process
3 | KWITCP CONFIRMATION
3.1 | Following last Post Install package completion, verify that the following 3 files are cleaned up :
1. update.bat 2. update2.bat 3. update6.bat
3.2 | Confirm these files are approx. 1k in size
3.3 | When file is opened in Notepad, you should only see "exit"

## POLLING SETUP
Coalition Store 6 - Set for Polling
v2.0
Store #:
Step: | Description | Notes | Completed By | Date/Time | POLLING TYPE SELECTION | ASSIGNMENT | MAINTAIN / REMOVE
[5 empty] | AS0 | QVC (ATRIUM) | REMOVE AFTER ROLLOUT
1 | Edit Store in Footprints |  |  |  | AS1 | QVC (ATRIUM) | REMOVE AFTER ROLLOUT
1.1 | Open Foot Prints and search store number in address book |  |  |  | AS2 | QVC (ATRIUM) | REMOVE AFTER ROLLOUT
1.2 | Select store number |  |  |  | AS3 | QVC (ATRIUM) | REMOVE AFTER ROLLOUT
1.3 | Edit store (top left) |  |  |  | AS4 | QVC (ATRIUM) | REMOVE AFTER ROLLOUT
[5 empty] | AS5 | QVC (ATRIUM) | REMOVE AFTER ROLLOUT
2 | Store Info |  |  |  | AS6 | QVC (ATRIUM) | REMOVE AFTER ROLLOUT
2.1 | Entering Store Info (address should already be present) |  |  |  | AS7 | QVC (ATRIUM) | REMOVE AFTER ROLLOUT
2.2 | Enter in Store Notes: |  |  |  | AS8 | QVC (ATRIUM) | REMOVE AFTER ROLLOUT
| Client Name - City, State (For Pandora – Include “Franchisee Point of Contact” for Escalations/Service Request Calls) Windows Key (By Register) mPOS Specific Info (# and Type of Apple Devices) |  |  |  | CO0 | COALITION DIAL-UP | DOES ANYONE STILL USE DIAL-UP?
2.3 | Enter IP Address (External/Public IP for Support Access) |  |  |  | CO1 | COALITION DIAL-UP | DOES ANYONE STILL USE DIAL-UP?
2.4 | Enter Polling Number (Type): ***Please see note below regarding mPOS-Only Stores*** |  |  |  | CO2 | COALITION DIAL-UP | DOES ANYONE STILL USE DIAL-UP?
| IP1 = East Coast/ UK IP2 = Central/Mountain IP3 = West Coast IP9/IP10 = Hawaii/ China |  |  |  | CO3 | COALITION DIAL-UP | DOES ANYONE STILL USE DIAL-UP?
2.5 | Credit Card Auth (Designate Type) |  |  |  | CO4 | COALITION DIAL-UP | DOES ANYONE STILL USE DIAL-UP?
2.6 | Merchant Services |  |  |  | CO5 | COALITION DIAL-UP | DOES ANYONE STILL USE DIAL-UP?
[5 empty] | CO6 | COALITION DIAL-UP | DOES ANYONE STILL USE DIAL-UP?
3 | Hardware Info |  |  |  | CO7 | COALITION DIAL-UP | DOES ANYONE STILL USE DIAL-UP?
| Register type/OS/Peripherals |  |  |  | CO8 | COALITION DIAL-UP | DOES ANYONE STILL USE DIAL-UP?
3.1 | Register Type (for mPOS Only store, select "mPOS Only") |  |  |  | CO9 | COALITION DIAL-UP | DOES ANYONE STILL USE DIAL-UP?
3.2 | Register OS |  |  |  | FT0 | VENETIAN | REMOVE NOW
3.3 | Register Qty |  |  |  | FT1 | VENETIAN | REMOVE NOW
3.4 | Monitor Type |  |  |  | FT2 | VENETIAN | REMOVE NOW
3.5 | Montitor Cable |  |  |  | FT3 | VENETIAN | REMOVE NOW
3.6 | Keyboard Type |  |  |  | FT4 | VENETIAN | REMOVE NOW
3.7 | Keyboard Cable |  |  |  | FT5 | VENETIAN | REMOVE NOW
3.8 | Receipt Printer Type |  |  |  | FT6 | VENETIAN | REMOVE NOW
3.9 | Receipt Printer Cable |  |  |  | FT7 | VENETIAN | REMOVE NOW
3.1 | Scanner HH Type (None, 7100, Sym300, mPOS) |  |  |  | FT8 | VENETIAN | REMOVE NOW
3.11 | Scanner HH Qty |  |  |  | FT9 | VENETIAN | REMOVE NOW
3.12 | Scanner - Reg Type (POS/Barcode Scanner) |  |  |  | IP0 | CHINA | MAINTAIN
3.13 | Scanner - Reg Qty |  |  |  | IP1 | EAST COAST / UK | MAINTAIN
[5 empty] | IP2 | CENTRAL / MOUNTAIN | MAINTAIN
4 | Download/Update Info |  |  |  | IP3 | WEST COAST | MAINTAIN
4.1 | Download Days: |  |  |  | IP4 | DO NOT USE | REMOVE IF NO RECORDS
| Highlight “sun – sat” |  |  |  | IP5 | DO NOT USE | REMOVE IF NO RECORDS
4.2 | Download Rank: |  |  |  | IP6 | DO NOT USE | REMOVE IF NO RECORDS
| 7 = East Coast 8 = Central/Mountain 9= West Coast 9= Hawaii/China |  |  |  | IP7 | DO NOT USE | REMOVE IF NO RECORDS
4.3 | Open/Live dates |  |  |  | IP8 | WAREHOUSE/LAB (POLL-ON-DEMAND) | MAINTAIN
4.4 | Nopoll_Report: |  |  |  | IP9 | HAWAII | MAINTAIN
| Yes = If the store is live today No = If the store is opening tomorrow/future date No = If this is an mPOS-Only Location |  |  |  | TR8 | KENNETH COLE (TZG) | MAINTAIN
[5 empty] | QAA | TESTING | MAINTAIN
5 | Save |  |  |  | QAC | TESTING | MAINTAIN
6 | Install Completion Email
6.1 | Select "Install Completion" Group:
Carlos Agosto cagosto@kwi.com DriveInstallGroup driveinstallgroup@kwi.com installgroup installgroup@kwi.com Retail Systems Services retailsystemsservices@kwi.com Victor Kahn vkahn@kwi.com, SSD@kwi.com
6.2 | Follow Format from "Guidelines" Tab
7 | Go-Live Email for Polling
7.1 | Select Go-Live Contacts:
“Go Live” Group: lchiappone@zellmangroup.com, ddenicola@zellmangroup.com Lisa Levine llevine@zellmangroup.com, Michael Wong mwong@kwi.com Steven Glickman sglickman@kwi.com Victor Kahn vkahn@kwi.com Felix Fikhman ffikhman@kwi.com, installgroup installgroup@kwi.com, ipadawer@kwi.com
7.2 | Subject = Store Name + Number Go Live
7.3 | Body = “Store Name + Number was installed today”
8 | Initial Install Spreadsheet under Go-Live tab
mPOS-Only Stores:
***Confirm whether mPOS-Only Store will be performing SOD/EOD each day (Opening and Closing the mPOS each day):
If Yes – Set as Correct Region (IP1, IP2, IP3, IP9):
IP1 = East Coast
IP2 = Central
IP3 = Mountain/West Coast
IP9 = Hawaii
If No – Set as IP8 (For “Poll-On-Demand)
RE: Trickle/Polling and EOD – Dev. - Handled for mPOS-Only stores via a Back Office Ticket; Wendy will open ticket (nothing for Install to do in this regard).
RE: CSI/L - Mike Wong - Install will send a request to Development to “set up a store” (Mike Wong will add it to Csi/l if it isn't already there) – this allows data to show on all Reports.

## VALIDATION
Coalition Store 6 - Validation
CLIENT NAME:
STORE # (VALIDATE PREFIX FOR CLIENT NAME):
STORE NAME:
STORE PHONE #:
STORE ADDRESS:
STORE COUNTRY:
STORE TYPE:
# OF REGISTERS (MATCH TILLS):
TAX RATE / TAX TABLE SET UP:
QAS:
DATE OF MASTER:
EXTERNAL/PUBLIC IP REG1:
EXTERNAL/PUBLIC IP REG2:
IP ADDRESS REG1:
IP ADDRESS REG2:
SUBNET:
GATEWAY:
DNS1:
DNS2:
COALITION VERSION:
OS:
BOARD-TYPE
AJB CREDIT, WEBAUTH, NON-INTEGRATED:
PINPAD MODEL:
PINPAD CONNECTION-TYPE:
AJB DEBIT:
PROFIT POINT GIFT CARDS:
TELECHECK CHECKS:
CONFIRM MERCHANT # FOR STORE IN XML:
POS PRINTER MODEL:
POS SCANNER MODEL:
CUSTOMER DISPLAYS:
MONARCH PRINTER MODEL:
DCN's
PLU/SKU
COUPONS (VALIDATE IF CLIENT UTILIZES > IF "YES" VAILDATE LOAD)
VALIDATE "POST-INSTALL" UPDATES

## LAST TRANS
Coalition Store 6 - "Last Trans" Process
Step: | Description
1 | Go to MySQL
1.1 | Navigate to Client Server
1.2 | Navigate to Client Name
2 | Query mySQL
2.1 | Paste query below into
select * from last_trans where stc_lt=440023;
3 | As a response, you will receive each Register #, and it's Last Transaction #
4 | Set Drive Transaction Number to the Last Trans for your Register # + 100
4.1 | Example:
If replacing Reg2 at 440023 -Return on Query would be:
Reg# Last Transaction Reg1 12099 Reg2 785 Reg3 55
You would make your Replacement drive's Transaction # 885.